## Summary
Link | https://toyotaasia.sharepoint.com/:x:/r/sites/ATLASCommunication/_layouts/15/Doc.aspx?sourcedoc=%7BDCE41278-97EB-439E-9B7A-80B34D97DF5D%7D&file=Summary%20Legacy%20Modify%20item.xlsx&action=default&mobileredirect=true&cid=4b9569bf-8f79-42d9-9b73-552419960e46 | [5 empty] | DB : DB Link |  |  | 1 : Impact Project Go Live (No workaround) | Initial : Draft from Planning Phase
[7 empty] | IF : Interface file |  | SAP : Support SAP | 2 : Impact Project Go Live (Have workaround) | In progress : Under confirm in DUR WS
[7 empty] | FN : Function |  | ENH : Internal Enhancement | 3 : Not impact Project Go Live | Confirmed : Confirm in DUR WS
Legacy List
# | LEGACY NAME | SAP RELATED | OTHER RELATED | Soruce | Destination | MODIFY ITEM | TYPE | DETAIL | PURPOSE | PRIORITY | STATUS | UPDATE BY | UPDATE DATE | Dev Status | Remark | Group
1 | MMS | BG |  | SAP | MMS | Receive Online Budget check | FN | Online Budget Check: New INV <- S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | INV
2 | MMS | BG |  | MMS | SAP | Fund Commitment | FN | Fund Commitment: New INV -> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | INV
3 | MMS | GL |  | FIS | MMS | Cost center Master function | DB | Receive I/F FIS -> New INV to synzc Cost Center | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | INV
4 | MMS | GL |  | MMS | FIS | Import Service Part data | DB | Send Import Service Part data | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | INV | ????
5 | MMS | GL |  | MMS | CPS | DM, ID, Local service part receive and supply | DB | Send DM, ID, Local service part receive and supply data | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | INV | ???
6 | MMS | INV |  | MMS | FIS | Non TMC Material Master (PIO, CBU_D) | IF | Function to generate Non TMC Material Master (PIO) (N001) notes (IF->FIS) | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | INV
7 | MMS | INV |  | MMS | SAP | Transfer JSP/MSP/JSP (EG+PIO) | IF | (IF05) Transfer JSP/MSP/JSP (EG+PIO) from GWH(1001) to PRD (3001) | SAP | 1 | In progress | Chutinthorn | 2023-05-22 |  |  | INV |  | https://toyotavn.sharepoint.com/:p:/r/sites/IT-SAP-Dev/_layouts/15/doc2.aspx?action=edit&sourcedoc=%7B0feef805-fd91-42f7-84f5-57a3dcff0df5%7D&wdOrigin=TEAMS-ELECTRON.teamsSdk.openFilePreview&wdExp=TEAMS-CONTROL&web=1
8 | MMS | INV |  | MMS | FIS | PIO, Import Part(GI internal) data | DB | Send data PIO, Import Part(GI internal), | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | INV
9 | MMS | MC | - | MMS | FIS | Inhouse Part Created (GR) Interface | IF | I/F Inhouse Part Created (GR): can provide w/ actual consumption Raw or not | SAP | 1 | In progress | DuongCT | 2023-05-17 |  |  | INV | ???? | #60
10 | Andon | MC | TPMS | Andon | TPMS | Prod. Plan | DB | I/F Andon send Prod. Plan to TPMS (for MPP I/F) | SAP | 1 | Confirmed | DuongCT | 2023-05-16 |  |  | Non-INV
11 | Andon | MC | TMC BOM | Andon | TPMS | Import Prod. Plan | FN | Receive I/F Prod. Plan send from Andon to TPMS (for MPP I/F) | SAP | 2 | Confirmed | DuongCT | 2023-05-16 |  |  | Non-INV
12 | Bank | AP |  | BANK | FIS | MT940 | DB | Send MT940 data | SAP | 1 | Confirmed | Chutinthorn | 2023-05-23 |  |  | Non-INV |  | OK, 2 interface with bank to get exrate
13 | Bank | AR |  | BANK | FIS | MT940 | IF | Send data MT940 | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  | confirm w/Hieu-san? | Non-INV |  | OK, 2 interface with bank to get exrate
14 | BMS | BG |  | BMS | SAP | WBS Budget Master​ | IF | WBS Budget Master​ BMS -> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
15 | BMS | BG |  | SAP | BMS | Budget Info Update | IF | Budget Info Update BMS <- S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
16 | BMS | GL |  | SAP | BMS | Receive Actual transaction (Direct GL posting) data | FN | Receive data of Actual transaction (Direct GL posting) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV |  | GIT | PXPS
17 | BTS | AP |  | BTS | SAP | Employee travelling and expense | IF | Send I/F Employee travelling and expenseL BTS -> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV |  | GR | MMS | MSP/JSP/IPO
18 | BTS | BG |  | SAP | BTS | Receive Online Budget check | FN | Online Budget Check: BTS <- S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV |  |  |  | CBU | FIS (TMSS)
19 | BTS | BG |  | BTS | SAP | Fund Commitment | FN | Fund Commitment: BTS -> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV |  | GI | FIS (source MMS)
20 | BTS | GL | FIS | FIS | BTS | Cost center Master function | DB | I/F FIS -> BTS to synzc Cost Center | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
21 | BTS | GL |  | FIS | SPP | Exchange rate daily | DB | Receive daily Exchange rate from (FIS/Convert Tool) | SAP | 2 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
22 | CPS | AA | - | SAP | CPS | Import Fixed Asset Master | FN | Receive IF Fixed Asset Master from SAP-AA | SAP | 1 | Confirmed | Chutinthorn | 2023-05-18 |  |  | Non-INV
23 | CPS | AP |  | SAP | CPS | Supplier Master | FN | Receive IF Fixed Asset Master from SAP-AA | SAP | 1 | Confirmed | Chutinthorn | 2023-05-18 |  |  | Non-INV
24 | CPS | AP |  | CPS | FIS | Local part , DM, In-DM , Direct AP invoice | DB | Send data of Local part , DM, In-DM , Direct AP invoice | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
25 | CPS | BG |  | SAP | CPS | Receive Online Budget check | FN | Online Budget Check: CPS <- S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
26 | CPS | BG |  | CPS | SAP | Fund Commitment | FN | Fund Commitment: CPS -> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
27 | CPS | GL |  | FIS | CPS | Cost center Master function | DB | Receive I/F FIS -> CPS to synzc Cost Center | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
28 | E-Invoice | AR |  | E-Invoice | FIS | AR Invoice (Vehicle & Service Part) | IF | Send data of AR Invoice (Vehicle&Service Part): e-Signature w/Invoice | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
29 | FIS | AP |  | SAP | FIS | Business Partner | FN | Receive IF BP Master from SAP | SAP | 1 | Confirmed | DuongCT | 2023-05-18 |  |  | Non-INV
30 | FIS | AP |  | FIS | SAP | Mapping table for BP Master | FN | Mapping function to map current FIS' BP with SAP' BP master | SAP | 1 | Confirmed | DuongCT | 2023-05-18 |  |  | Non-INV
31 | FIS | AP |  | SAP | FIS | Payment Request | FN | Receive Payment Request | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
32 | FIS | AP |  | FIS | SAP | AP Invoice (Non Procurment) interface | IF | Send I/F AP Invoice (non-procurement) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
33 | FIS | AP |  | FIS | SAP | Customs Invoice, Exporter AP Invoice interface | IF | Send I/F AP Invoice (Customs,Exporter AP Invoice) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
34 | FIS | AP |  | FIS | SAP | Import Part Invoice interface | IF | Send I/F Import Part Invoice | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
35 | FIS | AP |  | FIS | SAP | Local Part Invoice interface | IF | Send I/F Local Part Invoice | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
36 | FIS | AP |  | FIS | SAP | Import Service Part Invoice interface | IF | Send I/F Import Service Part Invoice | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
37 | FIS | AP |  | FIS | SAP | Direct/In-Direct Material Invoice | IF | Send I/F Direct/In-Direct Material Invoice | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
38 | FIS | AP |  | FIS | SAP | Direct AP invoice from PO non-INV interface | IF | Send I/F Direct AP invoice from PO non-INV | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
39 | FIS | AP |  | FIS | BANK | Send outgoing Payment Data | IF | Send Outgoing data to Bank | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
40 | FIS | AR |  | SAP | FIS | Receive AR transaction receive status | FN | Receive AR Transaction receive status | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
41 | FIS | AR |  | SAP | FIS | Dealer balance amount | FN | Receive Dealer balance amount | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
42 | FIS | AR |  | FIS | SAP | AR Sale Invoice (Veh INV) innterface | IF | Send I/F AR Sale Invoice (Veh INV) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
43 | FIS | AR |  | FIS | SAP | AR Sale Invoice (Non-INV) innterface | IF | Send I/F AR Sale Invoice (Non-INV) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
44 | FIS | AR |  | FIS | E-Invoice | Sale invoice w/ signature | IF | Sale invoice w/ signature | SAP | 1 | Initial | Chutinthorn | 2023-05-23 | Cancel |  | Non-INV
45 | FIS | AR |  | BANK | FIS | Receive MT940 data | FN | Receive MT 940 data | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  | confirm w/Hieu-san? | Non-INV
46 | FIS | GL |  | FIS | SAP | Bank Statement Interface | IF | Send I/F Bank Statement | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
47 | FIS | GL |  | FIS | SAP | Part Supply for DMO / IDM / SPR /Import SPR interface | IF | Send I/F Part Supply for DMO / IDM / SPR /Import SPR | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
48 | FIS | GL |  | FIS | SAP | Part Receive for DMO / IDM / SPR/Import SPR | IF | Send I/F Part Receive for DMO / IDM / SPR/Import SPR | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
49 | FIS | GL |  | FIS | SAP | Daily Exchange Rate | IF | Send I/F Daily Exchange Rate (new convert tool) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
50 | FIS | INV |  | FIS | SAP | Non TMC Material Master (PIO, CBU_D) | IF | Function to generate Non TMC Material Master (CBU_D) (N002) => Have to consider: Combine N001 with N002: Send from FIS ->SAP to utilize just only one I/F file ID | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
51 | FIS | INV |  | FIS | SAP | Update PDI Status | IF | Send I/F PDI Status | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
52 | FIS | INV |  | FIS | SAP | Domestic Veh Other Sales (CKD,CBU) | IF | Send I/F Domestic Veh Other Sales (CKD,CBU) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
53 | FIS | INV |  | FIS | SAP | Local Part Receive | IF | Send I/F Local Part Receive | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
54 | FIS | INV |  | FIS | SAP | Import Part Devan | IF | Send I/F Import Part Devan | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV | ???? | Cái này đã confirm từ MMS -> SAP
55 | FIS | INV |  | FIS | SAP | Import CBU Receiving (GIT) (Dummy Vehicle master and AP (1.1) – Dummy CBU, CBU | IF | Send I/F Import CBU Receiving (GIT) (Dummy Vehicle master and AP (1.1) – Dummy CBU, CBU | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
56 | FIS | INV |  | FIS | SAP | Update Pre PDI Status (Dummy) (GR-PO dummy CBU_D) – Dummy CBU | IF | Send I/F Update Pre PDI Status (Dummy) (GR-PO dummy CBU_D) – Dummy CBU | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
57 | FIS | INV |  | FIS | SAP | Inventory Good Receive (GR/GI) – CKD(GI Internal) Transfer SLOC for WIP | IF | Send I/F Inventory Good Receive (GR/GI) – CKD(GI Internal) Transfer SLOC for WIP | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
58 | FIS | INV |  | SAP | FIS | Receive Invoice CIF -Service Part | FN | Receive Invoice CIF -Service Part (FIS ->SPP) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV |  | Cái này phải sửa là SPP->FIS
59 | FIS | INV |  | FIS | SPP | Send Invoice information after IR to match with invoice in SPP | FN | Send Invoice information after IR to match with invoice in SPP | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
60 | FIS | MC |  | FIS | SAP | Goods Receipt (IH-P) | IF | Production Confirmation Interface (IH-P) (I/F Inhouse Part Created (GR): can provide w/ actual consumption Raw or not) | SAP | 1 | In progress | Chutinthorn | 2023-05-22 |  |  | Non-INV | ????? | =>#60
61 | FIS | MC |  | FIS | SAP | CKD Lineoff | IF | Line off data interface (CKD) | SAP | 1 | In progress | Chutinthorn | 2023-05-22 |  |  | Non-INV |  | #78
62 | FIS | PA |  | SAP | FIS | Cost center Master function | IF | Receive Cost Center Master | SAP | 1 | In progress | Chutinthorn | 2023-05-22 |  |  | Non-INV
63 | HR | AA | TFAST | HR | TFAST | Employee master Interface | IF | Send I/F Employee master HR-> TFAST | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
64 | HR | AA | TFAST | HR | TFAST | Org master Interface | IF | Send I/F Org master HR-> TFAST | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
65 | HR | AP |  | HR | SAP | Employee master | IF | Send I/F Employee master HR-> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
66 | HR | AP |  | HR | SAP | Org master | IF | Send I/F Org master HR-> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
67 | HR | AP |  | HR | SAP | Job Master | IF | Send I/F Job Master HR-> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
68 | HR | AP |  | HR | SAP | Payroll | IF | Send I/F Payroll HR-> S/4 | SAP | 1 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
69 | LSP | INV |  | LSP | FIS | Daily Order for Color Part | FN | Function to generate Order for Color Part (LSP): Workaround: User can user excel upload function to create daily order | ENH | 2 | Initial | DuongCT | 2023-05-18 |  |  | Non-INV
70 | LSP | INV |  | LSP | FIS | GRN: for other part (by LOT, Junbiki) | FN | Function to record actual receive for part (by LOT, Junbiki) Workaround: User can user excel upload function to record | ENH | 2 | Confirmed | DuongCT | 2023-05-23 |  |  | Non-INV
71 | PXPS | AP |  | PXPS | FIS | CKD Import Part Invoice | DB | Send data of CKD Import part Invoice | SAP | 1 | Confirmed | Chutinthorn | 2023-05-23 |  |  | Non-INV
72 | SPP | AP |  | SPP | FIS | Service Part Import Invoice | DB | Send data of Service part import invoice | SAP | 1 | Confirmed | Chutinthorn | 2023-05-23 |  |  | Non-INV
73 | SPP | GL |  | FIS | SPP | Exchange rate daily | DB | Receive daily Exchange rate from (FIS/Convert Tool) | SAP | 2 | Confirmed | DuongCT | 2023-05-18 |  |  | Non-INV |  | Lấy luôn từ convert tool???? => Không nên, vì user confirm trên FIS
74 | SPP | INV |  | SAP | SPP | Receive Invoice information after IR to match with invoice in SPP | FN | Receive Invoice information after IR to match with invoice in SPP (FIS ->SPP) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
75 | TEMS | AR |  | TEMS | FIS | Export part sales (Non-INV) data | DB | Send data of Export Part Sales (Non-INV) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
76 | TMSS | AR |  | TMSS | FIS | Vehicle sales data | DB | Send data of Vehicle Sales | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
77 | TMSS |  | FIS | TMSS | FIS | Goods Receipt (CKD,CBU) | DB | Production Confirmation data (CKD,CBU) | SAP | 1 | Confirmed | Chutinthorn | 2023-05-22 |  |  | Non-INV
78 | TMSS |  | FIS | TMSS | FIS | CKD Lineoff | DB | Line off data Data (CKD) | SAP | 1 | In progress | Chutinthorn | 2023-05-22 |  |  | Non-INV
79 | TOPSSE | AR |  | TOPSSE | FIS | Service Part sales(Non-INV) data | DB | Send data of Service Part sales (Non-INV) | SAP | 1 | Initial | Chutinthorn | 2023-05-23 |  |  | Non-INV
80 | TPMS | MC | TMC BOM | TPMS | TMC BOM | MPP Interface File | IF | Develop new IF of Production plan data (MPP) send to TMC BOM | SAP | 1 | Confirmed | Chutinthorn | 2023-05-16 |  |  | Non-INV
Note on F12: S_member: Đang khác với slide 8
Note on E59: S_member: MMS

## ATLAS_IF_DOC
Link | https://toyotavn.sharepoint.com/:p:/r/sites/IT-SAP-Dev/_layouts/15/doc2.aspx?action=edit&sourcedoc=%7B0feef805-fd91-42f7-84f5-57a3dcff0df5%7D&wdOrigin=TEAMS-ELECTRON.teamsSdk.openFilePreview&wdExp=TEAMS-CONTROL&web=1